## TestCase
TEST CASE
[8 empty] | PASS | 7
[8 empty] | FAIL | 4
[8 empty] | Not Executed | 1
[8 empty] | Out of Scope | 0
[8 empty] | TOTAL | 12
#SL | Test Case | Test Data | Step Description | Exepected Result | Actual Result | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 | Verify Input Field |  | 1.Go to othoba.com 2.Go to Login | Both Phone number and Password input field should be same in size | Input fields are not same | Input Field Size Error |  | Failed
2 | Email Verification | tt@56com | 1 Go to othoba.com | Email should be verified before creating an account | It takes wrong email. |  |  | Failed
2. Go to Login
3. Create Account
4. Enter Email
3 | Phone Number Verification | 1637815391 | 1. Go to othoba.com 2. Go to Login 3. Create Account 4. Enter Phone Number | Phone number should be verified before creating an account | It sends OTP code to phone number to verify. |  |  | Passed
4
5
|  | 1637815391 |  | An Error message should shown If same number is used | Message showed. |  |  | Passed
|  |  |  | Should show a warning message for the blank number field. | Message showed. |  |  | Passed
6 | Error Message Check |  |  | All character should be in same type. | Characters are not in same type |  |  | Passed
7 | Blank Field Check |  |  | should not remain blank and a warning message should show. | Showed warning message. |  |  | Passed
8 | Password Check |  |  | Password has to be used both character and number for security | It doesn't take both |  |  | Failed
9 |  | 1234 |  | Password must to be at least six numbers or shown a error message | Showed warning message. |  |  | Passed
10 |  | 12345678996777700 |  | Password should not be more thank eight characters or shown an error message | Didn't show an error message |  |  | Failed
11 |  | 12345 |  | Password should be matched or shown an error message | Error message showed |  |  | Passed
12 |  | abc@*123 |  | Password must has a special character or shown an error message | Error message didn't show |  |  | Not Executed

## Report
Test Case Report
Project Name - | Othoba.com
Module Name - | Login And Registration |  |  |  |  | Total No. | Status | Result :
Test Case Version | - |  |  |  |  | 7 | PASS
Written By | Tapu Saha |  |  |  |  | 4 | FAIL
Executed By | Tapu Saha |  |  |  |  | 1 | Not Executed | New Features | Testing Scope | Testing Environment :
Reviewed By | - |  |  |  |  | 0 | Out of Scope |  |  | Test Environment | Google Chrome Browser
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 7 | 4 | 1 | 0 | 12
Grand Total | 7 | 4 | 1 | 0 | 12
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.